## Phase 1
OPERATIONS AND MAINTENANCE FACILITY DATA REQUIREMENTS Process (O&M FDE)
Version 0.1, USACE Phase 1 Deployment Applicability: All Projects With Construction Contract Requirements
|  | PROJECT NAME | [INSERT PROJECT NAME] | PROJ. MGR | [NAME] | [P1] | 3 | OPEN ACTION BY PERSON
|  | LOCATION | [INSERT PROJECT LOCATION] | DT LEAD | [NAME] | [P2] | 5
|  | CONTRACT | [INSERT CONTRACT NUMBER] | PROJ. ENG | [NAME] | [P3] | 2
|  | TASK ORDER | [INSERT TASK ORDER IF APPLICABLE] |  |  |  | 31 | TOTAL OPEN ACTIONS
|  | BUILDING OCCUPANCY DATE | [DD-MMM-YY] |  |  |  | 0 | COMPLETED ACTION
|  | TODAY'S DATE | 2016-04-08 07:37 |  |  |  | 31 | TOTAL ACTIONS
| TASK | ACTIVITY | DESCRIPTION | LEAD | ACTION COMPLETION |  | POC | COMMENTS
| NUMBER | DECISION POINT |  | POSITION | DATE | COMMUNICATION | INITIALS | STATUS UPDATE
| - | USE DROP DOWN TO SELECT WHEN ACTION SHOULD BE COMPLTE | [DELETE THIS ROW PRIOR TO USE ON PROJECT] | USE DROP DOWN TO ASSIGN | INPUT COMPLETION DATE | ID HOW VERIFIED ACTION COMPLETE (eg SUBMITTAL EMAIL) | USE DROP DOWN TIED TO PN INITIALS | USE FOR COMMENTS FOR EACH ACTION ITEM
| 0 | PLANNING | A. Evaluate the applicablity of FDE requirements for Project. Inform PDT of ECB and/or Stakeholder requirements as applicable. | PM
***** Design Authorization *****
| 1 | DESIGN | A. Brief PDT and stakeholders on FDE requirements applicable to the project at project design kickoff. | PM
|  |  | B. Coordinate UFGS 01 78 24.00 10 requirements with relevant stakeholders. Ensure specification is appropriately edited, as needed. | TECH LEAD
|  |  | C. Tech Lead ensures editing and insertion of UFGS 01 78 24.00 10 ARMY FACILITY ELECTRONIC O&M DATA REQUIREMENTS in to project specifications. District Specification Writers, Technical Services, Construction Staff, CAD/BIM Manager, etc. may all be capable of providing input to this specifications. | TECH LEAD
|  |  | D. Review other project specifications as they relate to UFGS 01 78 24.00 10. Specifically review 01 33 00 SUBMITTAL PROCEDURES, 01 78 00 CLOSEOUT SUBMITTALS, AND 01 78 23 O&M DATA for coordination and accuracy. District Specification Writers, Technical Services, Construction Staff, CAD/BIM Manager, etc. may all be capable of providing input to these specifications. | TECH LEAD |  |  | [P2]
|  |  | E. Include UFGS 01 78 24.00 10 ARMY FACILITY ELECTRONIC O&M DATA REQUIREMENTS in all Quality Control activies related to the project. Coordinate resolution of all edits and comments. | TECH LEAD
***** Ready to Advertise *****
| 2 | SOLICITATION | A. Project is advertised for bids. | KO |  |  | [P1]
|  |  | B. Project Manager to address any relevant Bidder Inquiries specific to UFGS 01 78 24.00 10 ARMY FACILITY ELECTRONIC O&M DATA REQUIREMENTS requirements contained within solicitation. Coordinate responses with stakeholders and Tech Lead as required. | PM |  |  | [P2]
|  |  | C. Technical Lead coordinates with Project Manager and Specifications Section any amendments [if applicable] specific to UFGS 01 78 24.00 10 ARMY FACILITY ELECTRONIC O&M DATA REQUIREMENTS during solicitation. | TECH LEAD |  |  | [P2]
***** Authority to Award *****
| 3 | AWARD | A. Notify PDT of Project Award. | PM |  |  | [P1]
|  |  | B. Notify KTR of Award, Issue Notice to Proceed. | KO
***** Notice to Proceed *****
| 4 | PRECONSTRUCTION | A. During Pre-Construction Meeting/Post-Award Kickoff Meeting, discuss existence of FDE requirements in contractl per UFGS 01 78 24.00 10 ARMY FACILITY ELECTRONIC O&M DATA REQUIREMENTS. Establish date and time for O&M FD PxP Coordination Meeting to discuss detailed requirements. | KO |  |  |  | Discuss this with construction; may be flexible and be a part of BIM demonstration rather than project kickoff.
|  |  | B. KTR develops O&M FD PxP based on requirements within UFGS 01 78 24.00 10 OPERATIONS AND MAINTENANCE FACILITY DATA REQUIREMENTS. KTR may reference examples and resources on the CAD BIM center website. KTR submits O&M FD PxP to Government for review and approval. | KTR
|  |  | C. KO coordinates review and acceptance/rejection of O&M FD PxP. KO may consult district staff (via Tech Lead), stakeholders, and/or field personnel for review services. | KO
|  |  | D. Coordinate and conducts O&M FD PxP Coordination Meeting. Discuss required items as described in UFGS 01 78 24.00 10 ARMY FACILITY ELECTRONIC O&M DATA REQUIREMENTS. | KO/KTR
|  |  | E. KO accepts/rejects O&M FD PxP submittal. If accepted, proceed to task 5(A). If rejected, proceed to task 4(A). | KO
| 5 | CONSTRUCTION (Progress Submittal) | A. Contractor downloads FDW template from CAD-BIM website if not already obtained. | KTR
PENDING |  |  | B. Contractor and/or its sub-contractors populate FDW and FDS in compliance with UFGS 01 78 24.00 10 ARMY FACILITY ELECTRONIC O&M DATA REQUIREMENTS "Progress Submittal" requirements and as described in approved O&M FD PxP. KTR submits FDW and FDS for Government review and approval. | KTR |  |  | [P3]
PENDING |  |  | C. KO coordinates review and acceptance/rejection of progress FDW and progress FDS. KO may consult district staff (via Tech Lead), stakeholders, and/or field personnel for review services. | KO
|  |  | D. Coordinate and conduct Progress Submittal Coordination Meeting. Discuss required items as described in UFGS 01 78 24.00 10 ARMY FACILITY ELECTRONIC O&M DATA REQUIREMENTS. | KO/KTR
|  |  | E. (OPTIONAL) KO coordinates test conversion into GFEBS import template and possible test import into GFEBS depending upon quality and level of completion of Progress Submittal. KO may consult district staff (via Tech Lead) and/or stakeholders for test converstion and/or import. | KO
|  |  | F. KO accepts/rejects O&M FD PxP submittal. If accepted, proceed to task 6(A). If rejected, proceed to task 5(B). | KO
| 6 | CONSTRUCTION (Final Submittal) | A. KTR continues to populate/build FDW and FDS documents. | KTR |  |  | [P3]
|  |  | B.KTR performs QC/verification on FDW as specified in the approved PxP. | KTR
PENDING |  |  | C. After QC/verification of all FDW data in compliance with UFGS 01 78 24.00 10 ARMY FACILITY ELECTRONIC O&M DATA REQUIREMENTS "Final Submittal" requirements and as described in approved O&M FD PxP, KTR submits Final FDW for Government review and approval. This typically occurs during or after project Commissioning. | KTR |  |  | [P2]
|  |  | D. KO coordinates review and acceptance/rejection of Final FDW. KO may consult district staff (via Tech Lead), stakeholders, and/or field personnel for review services. | KO
|  |  | E. (OPTIONAL) KO coordinates test conversion into GFEBS import template and test import into GFEBS. KO may consult district staff (via Tech Lead) and/or stakeholders for test converstion and/or import. | KO
|  |  | F. KO organizes site verification meeting as part of commissioning process. | KO
|  |  | G. KO accepts/rejects Final FDW submittal. If accepted, proceed to task 7(A). If rejected, proceed to task 6(A). Once accepted, retain approved FDW in project files for compilation and turnover with approved FDS - usually completed after Beneficial Occupancy. | KO
***** Beneficial Occupancy Date *****
PENDING | 7 | PROJECT-CLOSEOUT | A. KTR continues to populate/build FDS documents in compliance with UFGS 01 78 24.00 10 ARMY FACILITY ELECTRONIC O&M DATA REQUIREMENTS "Final Submittal" requirements and as described in approved O&M FD PxP. | KTR |  |  | [P2]
|  |  | B.KTR performs QC/verification on FDS as specified in the approved PxP. | KTR
|  |  | C. After QC/verification of all FDS data in compliance with UFGS 01 78 24.00 10 ARMY FACILITY ELECTRONIC O&M DATA REQUIREMENTS "Final Submittal" requirements and as described in approved O&M FD PxP, KTR submits Final FDS for Government review and approval. This typically occurs after separate Government acceptance of project "As-Builts," since approved "As-Builts" are required as part of the Final FDS. | KTR
|  |  | D. KO coordinates review and acceptance/rejection of Final FDS. KO may consult district staff (via Tech Lead), stakeholders, and/or field personnel for review services. NOTE: FDS consists of an electronically compiled set of previously accepted "As-Builts" and O&M Manuals. Technical review requirements should be minimal as these submittals should be previously approved. | KO
|  |  | E. KO accepts/rejects Final FDS submittal. If accepted, proceed to task 7(F). If rejected, proceed to task 7(A). | KO
PENDING |  |  | F. KO packages approved Final FDW and Final FDS submittals with all other Contract Closeout deliverables (hardcopy O&M Manuals, As-Builts, GIS deliverables, etc.). Deliver to stakeholder for FDW upload/conversion into GFEBS, FDS archival for future reference. | KO |  |  | [P1]
***** Project Fiscal Complete *****

## Data Fields
TASK | ACTIVITY | DESCRIPTION | LEAD | ACTION COMPLETION |  | POC | COMMENTS
NUMBER | DECISION POINT |  | POSITION | DATE | COMMUNICATION | INITIALS | STATUS UPDATE
| PLANNNING |  | PM
| PRE-DESIGN |  | DT LEAD
| DESIGN |  | QA LEAD
| PEER/TECH REVIEW |  | PE
| SOLICITATION |  | KTR
| PRE-CONST. |  | AE PDT
| CONSTRUCTION |  | OWNER
| CLOSEOUT |  | USER
SPECS LEAD
TECH LEAD
KO
| POST-CLOSEOUT |  | BIM MGR